## Sheet1
id | SITE_ID | CIRCLE | Unique_SITE_ID | BAND | TOCO_NAME | OA_COMMERCIAL_TRAFFIC_PUT_ON_AIR_MS1_DATE | Project | Activity | Soft_AT_Status | SOFT_AT_ACCEPTANCE_DATE | SOFT_AT_ACCEPTANCE_MAIL | SOFT_AT_REJECTION_DATE | SOFT_AT_REJECTION_REASON | SOFT_AT_OFFERED_DATE | SOFT_AT_OFFERED_REMARKS | SOFT_AT_PENDING_REASON | SOFT_AT_PENDING_REMARK | SOFT_AT_PENDING_TAT_DATE | PHYSICAL_AT_Status | PHYSICAL_AT_ACCEPTANCE_DATE | PHYSICAL_AT_ACCEPTANCE_MAIL | PHYSICAL_AT_REJECTION_DATE | PHYSICAL_AT_REJECTION_REASON | PHYSICAL_AT_OFFERED_DATE | PHYSICAL_AT_OFFERED_REMARKS | PHYSICAL_AT_PENDING_REASON | PHYSICAL_AT_PENDING_REMARK | PHYSICAL_AT_PENDING_TAT_DATE | Performance_AT_Status | PERFORMANCE_AT_ACCEPTANCE_DATE | PERFORMANCE_AT_REJECTION_DATE | PERFORMANCE_AT_REJECTION_REASON | PERFORMANCE_AT_OFFERED_DATE | PERFORMANCE_AT_OFFERED_REMARKS | PERFORMANCE_AT_PENDING_REASON | PERFORMANCE_AT_PENDING_REMARK | PERFORMANCE_AT_PENDING_TAT_DATE | MAPA_STATUS
APAPNT13G1800_L900_L1800_L2300ATCulsRelocation | APNT13 | AP | APNT13 | G1800_L900_L1800_L2300 | ATC | 2022-08-14 00:00:00 | uls | Relocation | ACCEPTED | 2022-12-31 | dpr/dpr_acceptance_mail/soft_at/DPR_test_yOvAaMu.xlsx | [7 empty] | ACCEPTED | 2022-12-30 | dpr/dpr_acceptance_mail/physical_at/DPR_test_EBd1Fn5.xlsx | [7 empty] | ACCEPTED | 2022-12-30 | [5 empty] | L2300_PENDING,L1800_ACCEPTED,L900_ACCEPTED,G1800_ACCEPTED |  | NOT OK
APKOKD12G1800_L1800ATCCapacity UpgradeRelocation | KOKD12 | AP | KOKD12 | G1800_L1800 | ATC | 2022-08-14 00:00:00 | Capacity Upgrade | Relocation | [10 empty] | ACCEPTED | 2022-12-31 | dpr/dpr_acceptance_mail/physical_at/DPR_test_yVnI7MT.xlsx | [16 empty] | NOT OK
MUMBKD0072G1800_L1800ATCCapacity UpgradeRelocation | BKD0072 | MUM | BKD0072 | G1800_L1800 | ATC | 2022-07-25 00:00:00 | Capacity Upgrade | Relocation | [10 empty] | ACCEPTED | 2022-12-31 | dpr/dpr_acceptance_mail/physical_at/DPR_test_pkUMN6t.xlsx | [16 empty] | NOT OK
APBKD0071G1800_L1800ATCulsRelocation | BKD0071 | AP | BKD0071 | G1800_L1800 | ATC | 2022-07-25 00:00:00 | uls | Relocation | [29 empty] | NOT OK
APBKD0073G1800_L1800ATCRelocationRelocation | BKD0073 | AP | BKD0073 | G1800_L1800 | ATC | 2022-07-25 00:00:00 | Relocation | Relocation | [29 empty] | NOT OK
APBKD0074G1800_L1800ATCCapacity UpgradeRelocation | BKD0074 | AP | BKD0074 | G1800_L1800 | ATC | 2022-07-25 00:00:00 | Capacity Upgrade | Relocation | [29 empty] | NOT OK
MUMBKD0075G1800_L1800ATCNTRelocation | BKD0075 | MUM | BKD0075 | G1800_L1800 | ATC | 2022-07-25 00:00:00 | NT | Relocation | [29 empty] | NOT OK